## Backend
Event ERP project tasks ¦ Backend
Reviewed against the codebase on 20 Oct 2026. Source: project PRD.pdf and ERD.pdf.
PRD / ERD ID | Phase | Priority | Task to follow up | Status | Owner | Target date | Current coverage / done when
AUTH-BASE | Foundation | P0 | Keep the current login, session, profile, logout, and CSRF flow working. | Done |  |  | Session-based authentication is implemented. PRD calls for OAuth2/JWT with refresh-token rotation, so confirm whether the team will keep sessions or align with the PRD.
WEB-PLANS | Phase 1 | P0 | Serve the public plans, packages, and package contents. | Done |  |  | Public plan API is connected. Keep its response shape stable for the company profile.
CRM-LEADS | Phase 1 | P0 | Provide sales-scoped lead list and detail APIs with status, notes, date, location, package, and assignment updates. | Done |  |  | List/detail endpoints exist. Sales users are restricted to assigned leads; super users can assign sales-role users.
CRM-DASH | Phase 1 | P0 | Provide the sales dashboard summary, pipeline counts, recent leads, and sales performance. | Done |  |  | CRM dashboard endpoint is connected. It does not yet cover the broader ADM-003 executive metrics.
WEB-001 | Phase 1 | P0 | Add backend-managed portfolio, gallery, testimonials, and service content with publish/reorder support. | Done |  |  | Showcase entries now support services, gallery items, and testimonials with publish/reorder controls in Django admin and a public filtered API.
WEB-002 | Phase 1 | P0 | Capture event type, guest count, budget tier, and requirements; send an inquiry confirmation. | Done |  |  | Inquiry form and lead API capture event type, guest count, budget tier, and requirements. Confirmation email uses Django mail settings; local default logs to console, SMTP can be configured by environment.
WEB-003 | Phase 1 | P1 | Add Turnstile or equivalent bot checks and log/rate-limit abusive submissions. | To do |  |  | No bot verification or submission throttling is implemented.
CRM-001 | Phase 1 | P0 | Complete the CRM stages and pipeline behavior, including consultation, scheduled, quote sent, and won-to-event creation. | Done |  |  | The complete sales stage set is available. Sales can convert a Won lead into one linked event record; the conversion is idempotent and restricted to the assignee or super user.
CRM-002 | Phase 1 | P0 | Build customer history across leads, appointments, events, quotes, and invoices; add duplicate merge. | Blocked |  |  | History and super-user merge cover existing leads, converted events, and invoices. Appointment and quotation history depend on separate tasks that remain To do.
CRM-003/004 | Phase 1 | P0 | Build itemized quotations with totals, PDF export, version history, and client acceptance. | To do |  |  | Quotation and quotation-item models, APIs, and approval workflows are missing.
CRM-005 | Phase 1 | P1 | Require a standardized reason and notes before a lead can be marked Lost. | To do |  |  | Lost status can currently be saved without a loss reason.
APT-001/002 | Phase 1 | P0 | Add appointment scheduling, calendar views, status history, and staff conflict checks. | To do |  |  | Appointment app has no implemented domain model or API workflow.
EVT-001/002 | Phase 1 | P0 | Create event records from approved quotations and add milestones, tasks, assignments, and overdue alerts. | To do |  |  | The event app currently contains Plan, Package, and Content catalog models, not event projects or task management.
FIN-001 | Phase 1 | P0 | Add event-linked milestone invoices, due dates, sequential references, and balance tracking. | Blocked |  |  | Finance-only invoice APIs support event links, milestone labels, due dates, and sequential references. Balance/payment tracking requires the separate Payments task, left To do.
FIN-002 | Phase 1 | P0 | Record partial/full payments and update invoice balances and payment status. | To do |  |  | No payment model or payment API is implemented.
FIN-003 | Phase 1 | P0 | Implement configurable VAT, withholding, service charge, and exempt tax calculations. | Done |  |  | Invoices support multiple tax profiles per line, including VAT, withholding, service charge, and exemption. Inclusive/exclusive calculations and saved rate snapshots produce a separate breakdown.
ADM-001 | Phase 1 | P0 | Apply role and action permissions across every module and API. | Done |  |  | Every currently implemented API has an explicit public, authenticated, sales/super, or finance/super access policy. Modules with no APIs remain To do.
ADM-004 | Phase 1 | P1 | Add company, currency, timezone, calendar, and regional configuration. | To do |  |  | No organization settings model or API is present.
ERD-ALIGN | Foundation | P0 | Align domain models with the ERD, including Lead/customer qualification, Employee, Event, Quote, Appointment, Payment, and Expense relationships. | To do |  |  | Current Lead requires a Customer; ERD allows an unqualified lead without one. Invoice currently links to plan/package rather than Event. Employee and several ERD entities are absent.
NFR-SEC | Foundation | P0 | Set production authentication, HTTPS, secrets, encryption-at-rest, and backup/restore controls. | To do |  |  | Development uses Django sessions and DEBUG mode. Production TLS, encryption, backups, and restore runbooks are not established in the reviewed code.
APT-003 | Phase 1 | P1 | Add calendar invites or iCal/ICS synchronization for appointments. | To do |  |  | Depends on appointment scheduling.
EVT-003/004 | Phase 3 | P1 | Add run-of-show timelines and authorized post-contract scope amendments. | To do |  |  | Requires event and quotation workflows.
HR-001/002 | Phase 3 | P0 | Add staff/freelancer records and conflict-safe event shift assignments. | To do |  |  | HR app has no implemented domain models or APIs.
HR-003 | Phase 3 | P1 | Add leave approval and attendance/check-in records tied to shift payouts. | To do |  |  | Depends on workforce and shift records.
INV-001/002/003 | Phase 2 | P0 | Add asset catalog, availability reservations, checkout/return inspection, and damage records. | To do |  |  | Stock app has no implemented domain models or APIs.
INV-004 | Phase 2 | P1 | Add maintenance schedules that exclude unavailable assets from reservations. | To do |  |  | Depends on asset registry and reservation logic.
VND-001/002 | Phase 2 | P0 | Add vendor records, compliance details, purchase orders, items, and event commitments. | To do |  |  | Procurement app has no implemented domain models or APIs.
VND-003 | Phase 3 | P1 | Add post-event vendor scorecards and average ratings. | To do |  |  | Depends on vendor and event records.
FIN-004/005 | Phase 2 | P0 | Track event expenses and budgets, alert on overruns, and calculate event margin. | To do |  |  | Expense models, event cost tagging, and margin reporting are missing.
ADM-002 | Phase 3 | P0 | Add an append-only audit log for key state changes with actor, entity, timestamp, and before/after values. | To do |  |  | No audit log implementation was found.
ADM-003 | Phase 3 | P1 | Add date-filtered executive KPIs for active events, inquiries, receivables, and asset utilization. | Blocked |  |  | The date-filtered CRM dashboard includes lead KPIs and active event counts. Accurate receivables require Payments and asset utilization requires Inventory; both remain To do.
NFR-SCALE | Foundation | P1 | Measure API response times and validate the PRD concurrency targets. | To do |  |  | P95 latency and capacity targets have not been verified.
FUTURE | Future | P2 | Evaluate client/vendor portals, local payment gateways, SMS reminders, and predictive maintenance. | To do |  |  | Post-launch items from the PRD future roadmap.

## Frontend
Event ERP project tasks ¦ Frontend
Reviewed against the codebase on 20 Oct 2026. Source: project PRD.pdf and ERD.pdf.
PRD / ERD ID | Phase | Priority | Task to follow up | Status | Owner | Target date | Current coverage / done when
WEB-UI | Phase 1 | P0 | Keep the Orthodox Ethiopian event profile, plan/package showcase, and responsive visual design. | Done |  |  | The public company profile is implemented and loads the plan catalog from the backend.
AUTH-UI | Phase 1 | P0 | Keep login, session verification, and session-aware sign-out behavior aligned with the backend. | Done |  |  | Login page uses backend session auth; CSRF-aware requests are configured for lead updates.
CRM-UI | Phase 1 | P0 | Keep the CRM dashboard, filtered lead table, detail workspace, and lead update flow connected. | Done |  |  | Dashboard and lead pages are integrated. Detail view supports status, notes, date, location, package, and super-user sales assignment.
WEB-001 | Phase 1 | P0 | Add admin screens to manage portfolio items, galleries, testimonials, and services. | To do |  |  | Public profile currently showcases plans/packages; no content management screens exist.
WEB-002 | Phase 1 | P0 | Extend the inquiry form with event type, guest count, budget tier, and requirements; show confirmation state. | Done |  |  | Inquiry form captures event type, guest count, budget tier, and requirements and shows an enthusiastic confirmation state.
WEB-003 | Phase 1 | P1 | Add CAPTCHA/Turnstile feedback and accessible validation errors to the inquiry form. | To do |  |  | No bot challenge is present.
CRM-001 | Phase 1 | P0 | Add a drag-and-drop Kanban board for all PRD pipeline stages and prompt to create an event when Won. | Done |  |  | Kanban board supports every PRD lead stage. Moving a lead to Won prompts the user to create the linked event record.
CRM-002 | Phase 1 | P0 | Add unified customer profiles with inquiry/activity history and duplicate merge tools. | To do |  |  | Customer name and phone appear on lead detail only; no customer profile history or merge UI exists.
CRM-003 | Phase 1 | P0 | Build a multi-line quotation editor with totals, tax/discount display, and PDF download. | To do |  |  | No quotation UI is present.
CRM-004 | Phase 1 | P0 | Show quotation revisions and collect client acceptance/sign-off. | To do |  |  | Depends on quote versioning and approval APIs.
CRM-005 | Phase 1 | P1 | Require a loss reason and context when moving a lead to Lost. | To do |  |  | Current status control has no loss-reason flow.
APT-001/002 | Phase 1 | P0 | Add appointment calendar views, booking forms, statuses, and conflict warnings. | To do |  |  | No appointment screens are present.
APT-003 | Phase 1 | P1 | Show calendar invitation/sync actions for scheduled consultations. | To do |  |  | Depends on appointment and calendar APIs.
EVT-001/002 | Phase 1 | P0 | Add event setup and task/milestone boards with owners, due dates, dependencies, and overdue indicators. | To do |  |  | Current dashboard is sales-focused; there are no event or task screens.
FIN-001/002/003 | Phase 1 | P0 | Add invoice, milestone, payment receipt, balance, and tax views. | To do |  |  | No finance UI or invoice/payment API integration is present.
ADM-001 | Phase 1 | P0 | Guard routes and navigation by role and show clear permission feedback. | Done |  |  | CRM routes verify the session and sales/super role, show clear access feedback, and navigation lists only implemented CRM screens.
ADM-004 | Phase 1 | P1 | Add settings UI for company branding, currency, timezone, and regional preferences. | To do |  |  | Branding and date formatting are currently static.
EVT-003/004 | Phase 3 | P1 | Add mobile-friendly run-of-show and authorized scope-amendment screens. | To do |  |  | Depends on event operations workflows.
HR-001/002/003 | Phase 3 | P0 | Add staff directory, shift scheduling, leave, and attendance screens. | To do |  |  | No workforce UI is present.
INV-001/002/003/004 | Phase 2 | P0 | Add inventory catalog, availability/reservation, dispatch, return inspection, and maintenance screens. | To do |  |  | No inventory UI is present.
VND-001/002 | Phase 2 | P0 | Add vendor profiles and event-linked purchase order workflows. | To do |  |  | No vendor/procurement UI is present.
VND-003 | Phase 3 | P1 | Add vendor performance scorecard entry and review screens. | To do |  |  | Depends on vendor and event records.
FIN-004/005 | Phase 2 | P0 | Add event budget, cost, expense, and net margin views with overrun indicators. | To do |  |  | Depends on event and finance APIs.
ADM-002 | Phase 3 | P0 | Add an audit history view for permitted administrators. | To do |  |  | Depends on backend audit records and access rules.
ADM-003 | Phase 3 | P1 | Expand the CRM dashboard into date-filtered operational KPIs. | Blocked |  |  | Dashboard date filters apply to lead KPIs and active-event counts. Receivables and asset-utilization views await Payments and Inventory tasks, left To do.
NFR-LOCAL | Foundation | P1 | Add accessible interactions and configurable Amharic/English and local date/currency display. | To do |  |  | Current interface uses static English labels and fixed locale formatting.
FUTURE | Future | P2 | Add client/vendor portal, payment gateway, and SMS reminder screens when integrations are planned. | To do |  |  | Post-launch items from the PRD future roadmap.